## Template - Event Tasklist
Name | Owner/s | Due Date | Notes & Tips
Long Lead
Prepare Event Brief document
Book Venue |  |  | Ensure your venue is booked and confirmed before advertising the date
Begin creative research
Management Documentation
Budget - draft |  |  | Draft budget, and track ongoing expenses and revenue.
Task list |  |  | Prepare and allocate tasks to staff and volunteers
Event Plan - prepare draft |  |  | Prepare Event Plan and work on it ongoing up until closer to the event
Production Schedule |  |  | Prepare the production schedule, adding dates and times of scheduling of all supplier and programming activities. This can be split into 2 parts - bump in/out and show run.
Staff Roster |  |  | Decide what roles you need on the day, and prepare a staff and volunteer roster.
Staff Briefing |  |  | Prepare briefing for staff, including scheduling a time to brief staff either in advance or on the day.
Admin Tasklist |  |  | Prepare an admin tasklist, all the documents and information you need printed/available onsite.
Programming / Entertainment
Stage Programming
Research and book stage program
Book welcome to or acknowledgement of Country
Obtain Artist Tech Requirements and provide to AV supplier (see Suppliers)
Prepare stage running order
Book MC
Book Auslan interpreter (if required)
Prepare and send Auslan Script |  |  | Song lyrics, speech notes etc - the more information you can provide in advance the better
Obtain artist images and blurbs |  |  | For marketing and promotion
Send Marketing/Co Promotion info to performers |  |  | For extending your promotional reach to their networks
Allocate green rooms |  |  | Using timings from the stage program and information from performers, work out how much time prior to and after their performance they will need - how many people, are they doing more than 1 set etc.
Onsite Activities (Face painting, rides, activities)
Research and book activities/workshops
Roving Performers
Research and book roving performers
Obtain artist images and blurbs
Send Marketing/Co Promotion info to performers
Allocate green rooms
Send final briefing documents to all performers
Send final briefing documents to all performers and activity providers |  |  | Include event times, bump in and out/vehicle access information, green room allocations, stage running order, and other important relevant info
Stallholders - Internal & External
Create stallholder guidelines document |  |  | What are you seeking and your expectations. What is the event information they need to know.
Sent expression of interest to contacts |  |  | Who are you targeting to hold a stall?
Stallholder EOI closes
Respond to all - successful and unsuccessful
Enter all details onto contact sheet and infrastructure sheet
Create and send out invoices
Confirm all stallholders - paid/power/signage/PLI
Create & send final event information/guidelines document
Food Vendors / Catering
Create food vendor guidelines document |  |  | What is the event information they need to know.
Sent expression of interest to contacts |  |  | For a food vendor expression of interest and to collect the information you need. Include size of their vehicle/setup, menus, what dietaries they cater to, any images of their setup, their Food Trader registration number etc.
Food vendor EOI closes - remove tab form website
Respond to all - successful and unsuccessful
Enter all details onto contact sheet and infrastructure sheet
Send your approved list to Council's Environmental Health team
Create and send out invoices
Confirm all stallholders - paid/power/PLI/Menus/Statement of Trade (SOT)
Create & send final event information/guidelines document
Suppliers / Logistics
Audio/Visual/Production
Fencing
First Aid
Furniture
Infrastructure (Marquees)
Lighting
Photographer
Plant & Equip Hire
Power
Radio Hire
Safety Officer
Security
Staging
Staff & Volunteers
Toilets - including accessible and baby change facilities
Traffic Management
Videographer
Waste & Cleaning Services
Supplier Induction |  |  | Prepare a supplier induction for your event with all bump in/out, access, site rules, contacts and emergency information.
All Suppliers - send final information/supplier induction
Marketing
Develop Marketing Plan
Prepare FAQs |  |  | To be included on your webpage, which helps people find out more about your event and prepare their attendance
Graphic Design Brief - ROUND 1 |  |  | For any promotional elements needed for your event - posters, flyers, web & social media images etc.
Graphic Design Brief - ROUND 2 |  |  | For any onsite printed materials - signage, banners, flyers etc.
Signage Plan |  |  | Have a plan of what signage you need onsite to assist with wayfinding and information.
Website Brief/Update - ROUND 1 |  |  | Your initial event information to go on a webpage. To be coordinated with a 'launch date' in your Marcomms plan
Website Brief/Update - ROUND 2 |  |  | Any updates to your event information - inevitably as you get closer to your event you might have more details, such as program timings, ticket release info, FAQs, how to get there maps, event maps, food/catering info etc.
Website Brief/Update - ROUND 3 - Post event |  |  | How did your event go? What did it achieve? Include any photos and videos.
Create & send out co promo marketing pack |  |  | For promoting the event through your network of suppliers, performers, stallholders, food vendors etc.
Social Media Planner |  |  | A full plan of all your social media posts and any advertising, including the copy, images, hashtags, dates etc
Photographer |  |  | Professional photography of your event can be used to promote further iterations of the event. Consider how the images will be used in the future and select the most appropriate photographer for what you are trying to achieve.
Book photographer
Prepare photography brief
Receive photos and images (post event) |  |  | How are the images being used? You may need to update the website, social media, supply to media, supply to stakeholders etc.
Videographer |  |  | If required.
Book videographer
Prepare videography brief
Receive final video edit |  |  | What is the footage being used for? You may need to update the website, social media, supply to media, supply to stakeholders etc.
Prepare media release
Attendee Feedback Survey |  |  | How are you collecting feedback from your attendees? What do you want to know. How will you use that info. If preparing a survey, how will answers be collected (staff/signage/both). Book staff/prepare signage. A competition can be a good incentive to increase participation.
Safety Planning
Risk Assessment - prepare |  |  | For any size event, it is best practice to consider and prepare for and mitigate any hazards.
Prepare a draft
Meet with your team and discuss
Finalise
Emergency Management Plan - prepare
Traffic Management |  |  | Have you engaged traffic management? Ensure you receive copy of the Traffic Management Plan, as well as a copy of Vic Roads MOA & Council Approval (if applicable)
POPE Application |  |  | Does your event require a Place of Public Entertainment (POPE)?
Resident Notification |  |  | For major events, it is best practice to notify local residents of any activities that may impact them (traffic, noise etc). A resident notification is also required if you are required to get a POPE.
Emergency Services Notification |  |  | For major events, it is best practice to notify Emergency Services of your event, and key contacts, risks and emergency access information.
Public Liability Insurance |  |  | Collect & save PLI from all suppliers (including suppliers, performers, food vendors) - minimum $20 million cover is standard
SWMS or JSAs |  |  | Collect & save SWMS or JSAs from all suppliers performing high risk activities on your event site
Working with Children Checks |  |  | Collect & save WWCC from all performers/suppliers, if their role involves direct, unsupervised contact with children under 18 as part of child-related work
Schedule POPE Inspection |  |  | If a POPE is required, the building inspector will need to inspect your event setup, prior to your event start time.
Venue
Book venue
Liaise with venue throughout your planning |  |  | Your venue may require certain documentation in the lead up to your event. Ensure you know what is required and timelines.
Site maps |  |  | Prepare a site map of your event layout for your staff, suppliers, performers and food vendors. Include all key information.
Local trader liaison |  |  | Are there any local businesses nearby to your venue? What information can you provide or how can they be involved in your event?
Ticketing
Set up ticketing page
Decide and publish ticketing dates - On sale and cut off dates
Ticket monitoring |  |  | How are bookings/sales going? Do you need to promote any further?
Plan & roster ticketing entry staff
Create ticketing/foh staff briefing document
Create ticketing emails |  |  | What information/reminders do you want/need attendees to receive and when?
Staff & Volunteers
Decide on the roles you need to fulfil |  |  | Look at your event site. Where do you need staff? What roles will they fulfil?
Create staff roster & book staff
Create staff briefing document |  |  | What event information do you need them to know? What are your expectations?
Book in staff briefing |  |  | Brief staff
Accessibility
Create a Social Story and publish on the webpage |  |  | A social story is short, personalized narrative that explains a specific social situation, routine, or expectation in a clear, supportive way. They are used by people who are neurodiverse or have a disability to prepare for a situation.
Print Social Story |  |  | It is best practice to have some printed copies of social stories at the entry to your event
Sensory/Quiet space at the event |  |  | Can you include a sensory/quiet space at your event? What infrastructure/materials do you need? Promote this in your FAQs. Ensure you book a staff member to work at the space.
Create Sensory/Quiet Space Briefing document
Complete Event Accessibility Checklist
Post Event
Pay all invoices
Schedule a Debrief meeting |  |  | With your team.
Prepare Debrief |  |  | Prepare your debrief document in advance. Update it from discussion at your debrief meeting.
Stakeholder communication |  |  | Thank your stakeholders
Request, obtain & save medical report from First Aid supplier
Attendee feedback survey |  |  | Check the results from your survey. Include the information into your debrief. How will you use this information for your future project/event planning?
Finalise Budget