## Bump In-Out
2013 Children's Week Picnic PRODUCTION SCHEDULE | Event Name - Production Schedule Site Manager - Name - Mobile Number
DATE | Time | Action/ Item | Responsible | Note
Thursday 24 October 2013 | Day & Date
WEEK PRIOR
WEEK PRIOR
Thursday 24 October 2013 | Day & Date
Thursday 24 October 2013
Thursday 24 October 2013
Friday 25 October 2013 | Day & Date
Friday 25 October 2013
Friday 25 October 2013
Saturday 26 October 2013 | Day & Date
Saturday 26 October 2013
Day & Date
Sunday 27 October 2012
Sunday 27 October 2013
Sunday 27 October 2013
Sunday 27 October 2013 | Day & Date
Sunday 27 October 2013
Monday 28 October 2013
Monday 28 October 2013
Monday 28 October 2013
Monday 28 October 2013
Monday 28 October 2013
Monday 28 October 2013
Monday 28 October 2013

## Show Run
2013 Children's Week Picnic PRODUCTION SCHEDULE | Event Name - Production Schedule Site Manager - Name - Mobile Number
DATE | Time | Action/ Item | Responsible | Duration | Note
Thursday 24 October 2013 | Day & Date - SHOW RUN
WEEK PRIOR
WEEK PRIOR
Sunday 27 October 2012
Sunday 27 October 2013
Sunday 27 October 2013
Sunday 27 October 2013
Monday 28 October 2013
Monday 28 October 2013
Monday 28 October 2013
Monday 28 October 2013
Monday 28 October 2013
Monday 28 October 2013
Monday 28 October 2013

## EXAMPLE
2013 Children's Week Picnic PRODUCTION SCHEDULE | THE GREAT EVENT - Production Schedule Site Manager - BILLY BOB JONES - 0400 123 456
DATE | Time | Action/ Item | Responsible | Note
Thursday 24 October 2013 | Monday 4th September
WEEK PRIOR | 0800 | Arrive on site | Billy Bob All Staff | Site induction and mark up site layout
| 0900 | Supplier arrives for bump in | Jim's Marquee Company | Jim - 0400 789 123
WEEK PRIOR | 1700 | All suppliers and staff exit site | All
Thursday 24 October 2013 | Tuesday 5th September - BUMP IN
Thursday 24 October 2013 | 0800 | All staff arrive onsite | All
| 0815 | Staff Briefing | All | Meet at a certain point
| 0900 | Food trucks and stalklks bump in | Amal
| 1000 | All vehciles offsite | Safety Officer
| 1030 | Lots of other important information listed line by line
Thursday 24 October 2013 | 1100 | 1hr until Event Start - remind everyone | Event Manager
Friday 25 October 2013 | Tuesday 5th September - SHOW RUN
Friday 25 October 2013 | 1200 | START OF EVENT
| 1205 | Welcome to Country | 10mins
| 1215 | Dance Performance | 15mins
Friday 25 October 2013 | 1230 | Speeches | 15mins
| 1400 | Lots of other key items happening during your event line by line
| 1600 | END OF EVENT - Refer to Bump Out
Thursday 24 October 2013 | Tuesday 5th September - BUMP OUT
Thursday 24 October 2013 | 1630 | Check all attendees have left site
| 1630 | Begin vehcile bump out
| 1700 | Other key information listed line by line
Thursday 24 October 2013 | 1900 | All staff and vehcile offsite